## Sheet1
Week | Team Member | Position(s) | Task ID | Estimated Time | Time Required | Description
1 | Isaac | Technical Writing | 6 | 45 Minutes | 45 Minutes | BRD - Sections 1, 2, 3 (without 3.1) and 4
1 | Isaac | Technical Writing | 10 | 2 Hours | 2 Hours | Use case charts and editing
1 | Isaac | Database/Back-End | 15 | 1 hour (total) | 15 mins | database normalization/design
1 | Jacob | Technical Writing | 11 | 30 mins | 30 min | UML use cases ( C01 - C04 )
1 | Jacob | Technical Writing | 7 | 1 hour | 45 min | UML diagram
1 | Jacob | Technical Writing | 12 | 45 mins | 30 min | BRD - UML putting all use case together
1 | Jacob | Database/Back-End | 15 | 1 hour (total) | 15 mins | database normalization/design
1 | Brendon | Front-end | 13 | 15 mins | 15 mins | Initial website design
1 | Brendon | Front-end | 14 | 15 mins | 15 mins | UI Mockup
1 | Brendon | Technical Writing | 3 | 1 hour | 2 hours | Gantt Chart (1st Iteration)
1 | Ashleigh | Technical Writing | 17 | 45 mins | 45 mins | Weekly status report, task logs
1 | Ashleigh | Database/Back-End | 15 | 1 hour (total) | 15 mins | database normalization/design
1 | Ashleigh | Technical Writing | 9 | 30 mins | 30 mins | UML use case
1 | Ashleigh | Technical Writing | 4 | 30 mins | 30 mins | Project Charter
2 | Isaac | Database/Back-End |  | 1 hour | 1 hour | database normalization/design
2 | Isaac | Technical Writing |  | 1 hour | 1 hour | Updating BRD
2 | Jacob | DataBase/Back-End | 15 | 1 hour | 1 hour | database normalization/design
2 | Jacob | Techincal Writing | 11 | 1 hour | 30 mins | updating BRD usecases
2 | Jacob | Middleware | 26 | 8 hours | 3 hours | Web interface for entering products into database
2 | Brendon | Team Lead/Technical Writing
2 | Ashleigh | Front-end |  | 2 hours | 4 hours | Products page
3 | Isaac | Technical Writing |  | 1/2 hour | 1/2 hour | Configuring Gitlab and adding progress so far