## ICS199
Week | Team Member | Position(s) | Task ID | Estimated Time | Time Required | Description
1 | Isaac | Technical Writing | 6 | 45 Minutes | 45 Minutes | BRD - Sections 1, 2, 3 (without 3.1) and 4
1 | Isaac | Technical Writing | 10 | 2 Hours | 2 Hours | Use case charts and editing
1 | Isaac | Database/Back-End | 15 | 1 hour (total) | 15 mins | database normalization/design
1 | Jacob | Technical Writing | 11 | 30 mins | 30 min | UML use cases ( C01 - C04 )
1 | Jacob | Technical Writing | 7 | 1 hour | 45 min | UML diagram
1 | Jacob | Technical Writing | 12 | 45 mins | 30 min | BRD - UML putting all use case together
1 | Jacob | Database/Back-End | 15 | 1 hour (total) | 15 mins | database normalization/design
1 | Brendon | Front-end | 13 | 15 mins | 15 mins | Initial website design
1 | Brendon | Front-end | 14 | 15 mins | 15 mins | UI Mockup
1 | Brendon | Technical Writing | 3 | 1 hour | 2 hours | Gantt Chart (1st Iteration)
1 | Ashleigh | Technical Writing | 17 | 45 mins | 45 mins | Weekly status report, task logs
1 | Ashleigh | Database/Back-End | 15 | 1 hour (total) | 15 mins | database normalization/design
1 | Ashleigh | Technical Writing | 9 | 30 mins | 30 mins | UML use case
1 | Ashleigh | Technical Writing | 4 | 30 mins | 30 mins | Project Charter
2 | Isaac | Database/Back-End |  | 1 hour | 1 hour | database normalization/design
2 | Isaac | Technical Writing |  | 1 hour | 1 hour | Updating BRD
2 | Jacob | DataBase/Back-End | 15 | 1 hour | 1 hour | database normalization/design
2 | Jacob | Techincal Writing | 11 | 1 hour | 30 mins | updating BRD usecases
2 | Jacob | Middleware | 26 | 8 hours | 3 hours | Web interface for entering products into database
2 | Brendon | Team Lead/Technical Writing |  | 2 hours | 2 hours | Weekly status report, task logs
2 | Ashleigh | Front-end |  | 2 hours | 4 hours | Products page
3 | Isaac | Middleware |  | 5 hours | 5 hours | Working on the products list page
3 | Ashleigh | Front-end/minor middleware |  | 8 hours | 8 hours | Working on products list page, incorporating styles default page layout
3 | Brendon | Technical Writing |  | 1 hour | 1 hour | front end/directory restructuring
3 | Jacob | Middleware |  | 5 hours | 6 hours | Add product page updates categories-products table and renames and uploads images
4 | Ashleigh | Middleware/Database |  | 8 hours | 9.5 hours | single-view product page, registration page functionality, regular expressions on add product page, fix product selection page footer & navigation bar, consolidated duplicate pages
| Brendon | Front-end, middleware |  | 4 hours | 6 hours | invidual product page started, registration page creates new user, updated BRD with requirements change, provided add to cart functionality that also checks if user logged in
4 | Jacob | Front-end | 51 | 4 hours | 9 hours | registration page validation, populating DB. Fixed nav bar to show active.Validate addiing product
| Isaac | Front-End, Middleware/Database |  | 8 Hours | 7 Hours | log in page, validation, cart functionality, register page validation, search page, css on product page and cart page
5 | Jacob | Technical Writing Middleware/Database |  | 5 hours | 10 hours | Worked on privacy policy, Fixed log in bug. Project management docs
| Ashleigh |  |  | 2 hours | 2.5 hours | project management docs, payment pages
| Brendon | Front End,Technical Writing, Middleware |  | 3 hours | 2 hours | Minor CSS, updated BRD with new req., minor code tweak for usability
| Isaac | Front End, Technical Writing, Middleware |  | 8 hours | 6 hours | Minor CSS, added address box in registration, added backdrop for header, bug fixes, added last login functionality, built privacy policy functionality, wrote privacy policy, also added logout button
6 | Ashleigh
Brendon
Isaac
Jacob
7 | Ashleigh
Brendon
Isaac
Jacob

## BUS143
Week of: | Completed | Submitted |  | Team Member
May 28th | FALSE | FALSE
| TRUE | TRUE | Team Contract | Brendon
| TRUE | TRUE | Business Model Canvas | Ashleigh
| FALSE | FALSE
June 4th | FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
June 11th | FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
June 18th | FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
June 25th | FALSE | FALSE | EXAM WEEK
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE
| FALSE | FALSE